## Slide 1: Monroe County Community Integration Initiative
HSN November Update with
Maria O’Brien, Project lead for MC-CII

## Slide 2: Today’s Priorities
An intro (or recap) on what the CII project is, and who's on the team
What we’ve done since our last check in with HSN in July
What we’re planning on over the next year
Open discussion/questions

## Slide 3: What is CII?
CII, or the Community Integration Initiative, is a project sponsored by Monroe County, and facilitated by TogetherNow in partnership with DHS. The goal of the multi-year project is to assist DHS in the redesign of their service delivery model.
The CII team is a small project team within the TogetherNow group. It currently consists of a project lead, a community engagement team, and we're actively seeking a project manager.
This project utilizes human-centered design to get at the heart of what our community needs, and to involve the right people for the right solutions.

## Slide 4: CII Presentation HSN in July: Recap
Introduced our project
Talked about who we’re doing the work with
Explained our methodology
Provided a look at the Year 1 plan
Provided information on opportunities to engage in the work

## Slide 5: 2022 at a glance
Introduction with DHS team, contractor onboarding, space preparation, scope expansion.
Accomplishments
  Empathy Interviews Conducted with 75 DHS Staff Members Across Departments
  8 Focus Groups Conducted with CBO Staff
  DHS Staff Received Training In:
    Human Centered Design
    Human Services Value Curve
  CII Community Engagement Team has begun getting feedback from community members –
    Over 100 community members surveyed
    4 of 6 focus groups currently scheduled, 6 to be held by the end of December

## Slide 6: The Goals for 2023
Prototyping, and piloting with workgroups that consist of DHS workers, community members, and providers.
More integration into community! Connecting more community members to our project, gaining feedback across community on what’s working, and what isn’t.
Connecting the dots: Pulling together initiatives under TogetherNow that fit into this ecosystem. For ex: MyWayFinder, or the benefits calculator.

## Slide 7: How to reach us
Project Lead- Maria O’Brien
Maria.Obrien@systemsintegration.org
General Project Mailbox
transform@systemsintegration.org
Monroe County Community Integration Initiative Website
www.monroecounty.gov/cii
Provider Distribution List Sign-Up:
bit.ly/3EgdjW6